## Rating
| C TPAT BUSINESS PARTNERS RISK MAP |  |  |  |  | Document No: | EMS.AF.RA.001
[6 empty] | Approval Date: | 15.3.2026
[6 empty] | Revision No | 000
[6 empty] | Revision Date: | 00.00.0000
Scoring Matrix
[6 empty] | 1-3 | Low Security Risk
[6 empty] | 4-6 | Medium Security Risk
[6 empty] | >9 | High Security Risk
Service Provider | Service Received | Physical Risk (PR) | PR Score | Cyber ​​Security Risk (CSR) | CSR Skoru | Σ Risk Score | Risk Definition
DNM | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Realtex, | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Kipaş | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Cotton Fabric | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Odak | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Wdenim | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Nishat | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Bossa | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Çalık | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Recott | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Yedikardeşler | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Tüsa | Raw Material Supplier (Fabric) | Low | 1 | Low | 1 | 1 | Low Security Risk
Freudenberg | Raw Material Supplier (Interlining) | Low | 1 | Low | 1 | 1 | Low Security Risk
Haama | Raw Material Supplier (Pocketlining) | Low | 1 | Low | 1 | 1 | Low Security Risk
Özel Tela | Interlining - felt | Low | 1 | Low | 1 | 1 | Low Security Risk
Dizayn Etiket | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Yedi Kardeşler | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
YKK | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Kanaan | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Haksever | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Coats | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Trimco | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
SML | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Polsan | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Prym | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Dikmen Metal | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Turteks | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Moon Stone | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Check Point HK | Accessory Supplier | Low | 1 | Low | 1 | 1 | Low Security Risk
Al-Aziza | Personnel transportation service | Medium | 4 | Medium | 1 | 4 | Medium Security Risk
Creentech | IT Support Provider | Low | 1 | High | 3 | 3 | Low Security Risk

## Control
Scoring Matrix
1-3 | Low Security Risk
4-6 | Medium Security Risk
>9 | High Security Risk
1-3 | Low Security Risk | Tax Plate | Insurence Debt | 4-6 | Medium Security Risk | Tax Plate | Insurence Debt | Social Compliance Audit | C TPAT Self-Assessment
DNM | 1 | Suitable | Suitable | 4 | Al-Aziza | Suitable | Suitable | Not Applicable | Not Applicable
Realtex, | 1 | Suitable | Suitable
Kipaş | 1 | Suitable | Suitable | >9 | High Security Risk | Tax Plate | SGK Borcu | Social Compliance Audit | C TPAT Self-Assessment | C TPAT Training | C TPAT Controller
Cotton Fabric | 1 | Suitable | Suitable
Odak | 1 | Suitable | Suitable
Wdenim | 1 | Suitable | Suitable
Nishat | 1 | Suitable | Suitable
Bossa | 1 | Suitable | Suitable
Çalık | 1 | Suitable | Suitable
Recott | 1 | Suitable | Suitable
Yedikardeşler | 1 | Suitable | Suitable
Tüsa | 1 | Suitable | Suitable
Freudenberg | 1 | Suitable | Suitable
Haama | 1 | Suitable | Suitable
Özel Tela | 1 | Suitable | Suitable
Dizayn Etiket | 1 | Suitable | Suitable
Yedi Kardeşler | 1 | Suitable | Suitable
Kanaan | 1 | Suitable | Suitable
Haksever | 1 | Suitable | Suitable
Coats | 1 | Suitable | Suitable
Trimco | 1 | Suitable | Suitable
SML | 1 | Suitable | Suitable
Polsan | 1 | Suitable | Suitable
Prym | 1 | Suitable | Suitable
Dikmen Metal | 1 | Suitable | Suitable
Turteks | 1 | Suitable | Suitable
Moon Stone | 1 | Suitable | Suitable
Check Point HK | 1 | Suitable | Suitable
YKK | 1 | Suitable | Suitable
Creentech | 3 | Suitable | Suitable
Al-Aziza | 4 | Suitable | Suitable

## Risk Assesment EN
CTPAT Risk Assesment
NO | Hazard | Risk | Likelihood | Severity | Risk Score | Priority Level | Existing Control(s) | Corrective Action | DF | Responsible Person | Target Date | Statuse
1 | Breach of Perimeter Wall: Attempts by unauthorized individuals to enter the facility premises by climbing the 2.5-meter wall or exploiting weak points. | Unauthorized entry | 2 | 4 | 8 | Medium | 1. Perimeter wall height of 2.5 meters 2. Perimeter wall lighting 3. 24-hour monitoring with security cameras 4. Continuous 24-hour camera surveillance | All employees will receive CTPAT security awareness training, and the implementation of the system will be monitored through regular security audits. |  | Sustainability Department | 2025-12-15 | Complated
2 | Unauthorized Entry Through Main or Shipping Gates: Individuals or vehicles entering without ID verification or bypassing gate security. | Unauthorized access through the gate | 2 | 5 | 10 | Medium | 1. ID verification 2. Visitor registration 3. Presence of security personnel 24/7 | Existing controls will be maintained, and system compliance will be verified through quarterly security audits. |  | Security & Sustainability Department | 2025-12-01 | Complated
3 | Unauthorized Access to Internal Areas Due to Misuse or Loss of Employee ID Cards: Sharing, theft, or loss of cards leading to unauthorized access to sensitive areas. | Unauthorized access to internal areas | 1 | 4 | 4 | Low | 1. Training of employees 2. Use of authorized IDs for access to sensitive areas | A lost card procedure will be established, and all employee cards will be assigned and issued to personnel. |  | HR & IT | 2025-12-20 | Complated
4 | Visitors Moving Unsupervised Within the Facility: Visitors entering production, warehouse, or restricted areas without proper escort. | Unsupervised visitor movement | 1 | 3 | 3 | Low | 1. Visitor ID card 2. Escorting visitors to the person/department they are visiting 3. Recording unauthorized access to restricted areas | An automatic door will be installed at the finished goods warehouse. |  | All Departments | 2025-12-15 | Complated
5 | Theft or Unauthorized Activity in Warehouse or Shipping Areas: Unauthorized interference with products, removal of goods, or risk of illegal additions. | Interference with shipment | 3 | 5 | 15 | High | 1. Seal 2. CCTV recordings 3. Security escort during loading | Existing controls will be maintained, and a 9-step container inspection form will be established. |  | Warehouse Supervisor | 2025-12-01 | Complated
6 | Misrouting, Theft, or Diversion of Products During Loading or Shipment: Cargo being loaded onto the wrong vehicle, misdirected, or accessed by unauthorized individuals. | Shipment diversion | 2 | 4 | 8 | Medium | 1. Driver verification 2. CCTV recordings 3. Security escort during loading | Existing controls will be maintained, and system compliance will be regularly audited. |  | Logistics | Continuous | Continuous
7 | Use of Incorrect or Unverified Trailer/Container: Trailer number mismatch, trailer swaps, or use of fraudulent vehicles. | Container/trailer swap | 1 | 5 | 5 | Low | 1. Gate logs 2. Indicating the container number in the received declaration/undertaking. | Making prior license plate notification mandatory. |  | Logistics & Security | Continuous | Continuous
8 | Tampering or Counterfeiting of Security Seals: Cutting, replacing, or using fake seals. | Seal tampering | 3 | 4 | 12 | High | 1. Seal records 2. Customs officer approval | Existing controls will be maintained, and system compliance will be regularly audited. |  | Logistics & Warehouse | Continuous | Continuous
9 | Unauthorized Digital Access to Systems Containing Operational or Shipment Data: Weak passwords, unauthorized logins, or system vulnerabilities. | Data breach | 2 | 3 | 6 | Low | 1.Password procedure 2. Training | CTPAT cybersecurity training will be provided to computer users, and passwords will be required to be changed every three months. |  | IT | 2025-12-10 | Complated
10 | Attempts to Breach Systems Through Phishing, Malware, or Social Engineering: Gaining system access by deceiving personnel. | Cyberattack | 3 | 4 | 12 | High | 1. Firewall, antivirüs 2. IT procedures | CTPAT cybersecurity training will be provided to computer users. |  | IT | 2025-12-10 | Complated
11 | Employment of High-Risk Personnel Due to Insufficient Background Screening: Failure to identify employees who may pose internal security risks. | Insider risk | 2 | 3 | 6 | Low | 1. Reference checks 2. Hiring and termination procedures | Existing controls will be maintained. System adequacy will be audited at least once a year by the Social Performance Team. |  | HR | Continuous | Continuous
12 | Insufficient Security Awareness Among Employees: Failure to notice or report suspicious behaviors. | Low security awareness | 3 | 3 | 9 | Medium | 1. Orientation training 2. Providing CTPAT security awareness training at least once a year 3. Training procedure | All trainings will be completed. |  | HR & Sustainability Department | 2025-12-10 | Continuous
13 | Unauthorized Entry into Finished Goods Warehouse and Metal Detector Areas: Risk of product interference or manipulation. | Production area and product risk | 2 | 5 | 10 | Medium | 1.Restricted access 2. Trainings | Blind spot analysis of CCTV and camera layout assessment will be conducted. |  | IT and Final product warehouse manager | 2025-12-10 | Complated
14 | Unauthorized Access to the Wastewater Treatment Plant or Chemical Storage Area: Risk of chemical tampering, sabotage, or environmental hazards. | Wastewater treatment and chemical area risk | 2 | 4 | 8 | Medium | 1. Locked area 2. Identification and assignment of department responsible | Existing controls will be maintained. System adequacy will be audited through monthly internal audits. |  | Sustainability Department | Continuous | Continuous
15 | Working with Suppliers, Transporters, or Service Providers with Inadequate Security Levels: Increased opportunity for illegal interference within the supply chain. | Supplier risk | 1 | 3 | 3 | Low | 1. Approved supplier list 2. Supplier risk assessment 3. Supplier selection procedure | Existing controls will be maintained. |  | Purchase | Continuous | Continuous
16 | Failure to Report or Escalate Security Incidents in a Timely Manner: Late detection of breaches, loss of evidence, and creation of security vulnerabilities. | Existing controls will be maintained | 4 | 5 | 20 | Very High | 1. Providing CTPAT security awareness training at least once a year 2. Security policy and procedure | Training will be completed for all personnel, and the security policy and procedure will be posted on announce boards. |  | Security & Sustainability Department | 2025-12-10 | Complated
17 | Access Rights Not Revoked for Employees Who Leave the Company: Risk of misuse of turnstiles, doors, and access systems by former personnel. | Facility security risk | 2 | 4 | 8 | Medium | 1. Card deactivation upon exit, security briefing | Digital access logs should be checked, and the employee’s ID card should be collected using a card assignment form. |  | HR / Security | 2025-12-20 | Complated
18 | Loss or Unauthorized Possession of Keys for Critical Areas: Security gaps caused by keys for the warehouse, metal detector area, server room, or CCTV room falling out of controlled access. | Unauthorized access | 2 | 3 | 6 | Low | 1. Key inventory list 2. Key handover form 3. Key security procedure 4. Daily security checklist | Existing controls will be maintained. |  | Security | Continuous | Continuous
19 | Malfunctioning Outdoor Lighting Leading to Shadowed or Dark Areas: Reduced visibility in the yard, parking lot, and building perimeter, increasing blind spots for security cameras. | Creation of dark areas, security breach risk | 3 | 3 | 9 | Medium | 1. 24-hour monitoring with camera system for real-time detection 2. Connecting the lighting system to a generator 3. Regular site patrols | Existing controls will be maintained. |  | Security | Continuous | Continuous
20 | Risk of Forklifts Colliding with Employees, Visitors, or Cameras: Potential accidents due to speed, limited visibility, or inadequate separation between pedestrians and vehicles during material handling. | Security camera system failure | 1 | 4 | 4 | Low | 1. Audible alarm and sensor system 2.Forklift training 3. 24-hour camera monitoring | Pedestrian pathways should be marked, and a camera maintenance plan should be established. |  | IT & Security | 2025-12-20 | Complated
21 | Metal Parts Contaminating the Product in the Production Area: Needles, machine parts, or metal fragments compromising product integrity and customer safety. | Product and customer safety breach | 2 | 5 | 10 | Medium | 1. Metal detector 2. Regular calibrations 3. Daily routine checks (every 2 hours) | Existing controls will be maintained. |  | Quality and Final product warehouse manager | Continuous | Continuous
22 | Unauthorized Access to the Server Room Leading to Compromised Data Security and System Integrity: Tampering, sabotage, or data theft involving critical IT systems. | Critical data/security access risk | 1 | 5 | 5 | Low | 1. Locked room 2. Authorized personnel only | Existing controls will be maintained. |  | IT | Continuous | Continuous
23 | Assignment of Inappropriate Personnel to Security-Critical Positions: Individuals with insufficient security backgrounds being appointed to sensitive roles such as security, logistics, shipping, metal detector operators, or IT. | Incorrect personnel assigned to critical roles | 2 | 4 | 8 | Medium | 1. Reference checks 2. Identity verification 3. Renewal of criminal record every 6 months 4. Hiring and termination procedures | Existing controls will be maintained. |  | HR | Continuous | Continuous
24 | Inability to Verify the Accuracy of the Truck Arriving for Shipment: License plate mismatches, loading onto the wrong vehicle, or fraudulent transportation attempts. | Cargo loaded onto the wrong vehicle, product loss, security risk | 1 | 4 | 4 | Low | 1. Vehicle license plate verification | Making prior license plate notification mandatory. |  | Logistics | Now | Complated
25 | Risk of Suspicious Packages, Fake Couriers, or Package Swapping in Cargo Deliveries: Lack of proper control over small packages delivered to the facility. | Suspicious package, fake courier, package tampering risk | 2 | 3 | 6 | Low | 1. Cargo logbook 2. Security check 3. Cargo and visitor procedure | Existing controls will be maintained, and system continuity should be audited during quarterly security inspections. |  | Security | Continuous | Continuous
26 | Container sealing | Unauthorized items inserted into shipment | 2 | 4 | 12 | High | 7-point container inspection, CCTV monitoring | Reinforce inspection procedures, train staff |  | Logistics Manager | Continuous | Complated
27 | Seal tampering or replacement | Seal broken or replaced | 2 | 4 | 12 | High | High Security Seals, seal number recorded | Verify seals at loading and port |  | Warehouse Supervisor | Continuous | Complated
28 | Cargo theft | Loss of shipment during transport | 3 | 3 | 9 | Medium | Approved transport company, GPS tracking | Enhance GPS monitoring and route security |  | Transport Coordinator | Continuous | Complated
29 | Unauthorized stops | Truck stops at unapproved locations | 3 | 3 | 9 | Medium | Defined approved stops | Enforce route compliance, driver training |  | Transport Coordinator | Continuous | Complated
30 | Document fraud | Falsification or alteration of shipping documents | 2 | 4 | 8 | Medium | Document verification before handover | Implement double-checking of documents |  | Shipping Admin | Continuous | Complated
31 | Unauthorized access | Unauthorized persons approaching cargo | 2 | 3 | 6 | Low | Secured loading area, monitored by CCTV | Improve fencing and access control |  | Security chief | Continuous | Complated
32
33
34
35

## Risk Değerlendirmesi TR
CTPAT Risk Değerlendirmesi
NO | Tehlike | Risk | Olasılık | Şiddet | Risk Puanı | Önem Derecesi | Mevcut Önlem | Aksiyon | DF | Sorumlu | Termin
1 | Bahçe Duvarının İhlal Edilmesi: 2.5 metrelik duvara tırmanılması veya zayıf noktaların kullanılması ile yetkisiz kişilerin tesis alanına girmeye çalışması. | Yetkisiz giriş | 2 | 4 | 8 | Orta | 1. Bahçe duvarının 2.5 m olması 2. Bahçe duvarı aydınlatması 3. Güvenlik kameraları ile 24 saat izlenmesi 4. 24 saat kamera ile izlenmesi | Tüm çalışanlara CTPAT güvenlik farkındalığı eğitimlerinin verilecek ve düzenlik güvenlik denetimleriyle sistemin uygulanabilirliği denetlenecek |  | Sürdürülebilirlik Departmanı | 2025-12-15
2 | Ana veya Sevkiyat Kapılarından Yetkisiz Giriş: Kimlik kontrolü yapılmadan kişi veya araçların giriş sağlaması, kapı güvenliğinin atlatılması. | Kapıdan yetkisiz erişim | 2 | 5 | 10 | Orta | 1. Kimlik kontrolü, 2. Ziyaretçi kaydı 3. 24 saat güvenlik ekibinin bulunması | Mevcut önlemlere devam edilecek ve sistemin uygunluğu 3 aylık güvenlik denetimleri ile denetlenecek |  | Güvenlik & Sürdürülebilirlik Departmanı | 2025-12-01
3 | Personel Kartlarının Kötüye Kullanımı veya Kaybı Nedeniyle İç Alanlara Yetkisiz Erişim: Kartların paylaşılması, çalınması veya kaybolması nedeniyle hassas alanlara izinsiz giriş sağlanması. | İç alanlara izinsiz giriş | 1 | 4 | 4 | Düşük | 1. Çalışanların eğitilmesi 2. Hashas alanları giriş için görevli ID kullanılması | Kayıp kart prosedürü yazılacak, tüm personel kartları zimmetlenerek çalışana verilecek |  | IK & IT | 2025-12-20
4 | Ziyaretçilerin Tesis İçerisinde Kontrolsüz Dolaşması: Ziyaretçilerin üretim, depo veya kısıtlı alanlara refakatsiz girmesi. | Kontrolsüz ziyaret | 1 | 3 | 3 | Düşük | 1. Ziyaretçi kartı 2. Ziyaretçinin ziyaret ettiği kişi/birime kadar eşlik edilmesi 3. Kısıtlı alana yetkisiz kişilerin girişlerinin kaydedilmesi | Son ürün depoya otomatik kapı montajı yapılacak |  | Tüm Departmanlar | 2025-12-15
5 | Depo veya Sevkiyat Alanlarında Hırsızlık veya Yetkisiz İşlem Yapılması: Ürünlere izinsiz müdahale, ürün çıkarma veya yasa dışı ekleme riski. | Sevkiyata müdahale | 3 | 5 | 15 | Yüksek | 1. Mühür, 2. CCTV kayıtları 3. Yükleme boyunca güvenliğin eşlik etmesi | Mevcut önlemlere devam edilecek ve 9 adımlı konteyner kontrol formu oluşturulacak. |  | Depo Şefi | 2025-12-01
6 | Yükleme veya Sevkiyat Sırasında Ürün Yönlendirme Hatası, Çalınma veya Sapma: Yükün yanlış araca verilmesi veya yönlendirilmesi, yetkisiz kişilerce erişilmesi. | Sevkiyat sapması | 2 | 4 | 8 | Orta | 1. Şoför doğrulama 2. CCTV kayıtları 3. Yükleme boyunca güvenliğin eşlik etmesi | Mevcut önlemlere devam edilecek ve sistemin uygunluğu düzenli olarak denetlenecek |  | Lojistik | Sürekli
7 | Yanlış veya Doğrulanmamış Treyler/Konteyner Kullanımı: Treyler numarası eşleşmemesi, treyler değişimi veya sahte araç kullanımı. | Konteyner değişimi | 1 | 5 | 5 | Düşük | 1. Kapı kayıtları 2. Alınan ikrarda konteyner numarasının belirtilmesi | Önceden plaka bildirimi zorunlu hale getirme |  | Lojistik & Güvenlik | Hemen
8 | Güvenlik Mühürlerinin Manipülasyonu veya Sahteciliği: Mühürlerin kesilmesi, değiştirilmesi, sahte mühür kullanılması. | Mühür manipülasyonu | 3 | 4 | 12 | Yüksek | 1. Mühür kayıtları 2. Gümrük memur onayı | Mevcut önlemlere devam edilecek ve sistemin uygunluğu düzenli olarak denetlenecek |  | Lojistik & Depo | Sürekli
9 | Operasyonel veya Sevkiyat Verilerinin Bulunduğu Sistemlere Yetkisiz Dijital Erişim: Zayıf şifreler, izinsiz kullanıcı girişleri veya sistem açıkları. | Veri ihlali | 2 | 3 | 6 | Düşük | 1.Parola prosedürü 2. Eğitim | Bilgisayar kullanıcılarına CTPAT siber güvenlik eğitimi verilecek. Şifrelerin her 3 ayda bir değiştirilmesi sağlanacak |  | IT | 2025-12-10
10 | Phishing, Malware veya Sosyal Mühendislik Yoluyla Sistemlere Sızma Girişimleri: Personelin kandırılmasıyla sistemlere erişim sağlanması. | Siber saldırı | 3 | 4 | 12 | Yüksek | 1. Firewall, antivirüs 2. IT prosedürleri | Bilgisayar kullanıcılarına CTPAT siber güvenlik eğitimi verilecek. |  | IT | 2025-12-10
11 | Yetersiz Arka Plan Kontrolü ile Yüksek Riskli Personelin İstihdamı: İç güvenlik riski oluşturabilecek çalışanların fark edilmemesi. | İç risk | 2 | 3 | 6 | Düşük | 1. Referans kontrolü 2. İşe alım ve işten çıkarma prosedürü | Mevcut önlemlere devam edilecektir. Sistemin yeterliliği, en az yılda 1 kez Sosyal Performans Takımı ile denetlenecektir. |  | IK | Sürekli
12 | Çalışanlarda Güvenlik Farkındalığının Yetersiz Olması: Şüpheli davranışların bildirilmemesi veya fark edilmemesi. | Düşük farkındalık | 3 | 3 | 9 | Orta | 1. Oryantasyon eğitimleri 2. Yılda en az 1 kez CTPAT güvenlik farkındalık eğitiminin verilmesi 3. Eğitim prosedürü | Tüm eğitimler tamamlanacak |  | IK & Sürdürülebilirlik | 2025-12-10
13 | Son Ürün Depo ve Metal Dedektör Alanlarına Yetkisiz Giriş: Ürünlere müdahale edilmesi veya manipülasyon riski. | Üretim alanı ve ürün riski | 2 | 5 | 10 | Orta | 1.Kısıtlı erişim 2. Eğitimler | CCTV kör nokta analizi ve kamera layoutunun alınması |  | IT ve Son ürün depo müdürü | 2025-12-10
14 | Arıtma Tesisi veya Kimyasal Depolama Alanına Yetkisiz Giriş: Kimyasal müdahale, sabotaj veya çevresel risk oluşumu. | Arıtma ve kimyasal alanı riski | 2 | 4 | 8 | Orta | 1. Kilitli alan 2. Bölüm sorumlusunun tanımlanması ve görevlendirilmesi | Mevcut önlemlere devam edilecektir. Sistemin yeterliliği aylık iç denetimle ile denetlenecektir |  | Sürdürülebilirlik Departmanı | Sürekli
15 | Güvenlik Seviyesi Yetersiz Tedarikçi, Nakliyeci veya Hizmet Sağlayıcılar ile Çalışma: Supply chain içine yasa dışı müdahale imkanının oluşması. | Tedarikçi riski | 1 | 3 | 3 | Düşük | 1. Onaylı tedarikçi listesi 2. Tedarikçi risk değerlendirmesi 3. Tedarikçi seçim prosedürü | Mevcut önlemlere devam edilecektir. |  | Satınalma | Sürekli
16 | Güvenlik Olaylarının Zamanında Bildirilmemesi veya Eskale Edilmemesi: İhlallerin geç fark edilmesi, delil kaybı ve güvenlik açığı oluşması. | Mevcut önlemlere devam edilecektir. | 4 | 5 | 20 | Kritik | 1. Yılda en az 1 kez CTPAT güvenlik farkındalık eğitiminin verilmesi 2. Güvenlik politikası ve prosedürü | Tüm personeller için eğitim tamamlanacak ve güvenlik politika ve prosedürü duyuru panolarında asılacak |  | Güvenlik & Sürdürülebilirlik | 2025-12-10
17 | İşten ayrılan personelin erişim hakları iptal edilmemesi: Turnike, kapı ve erişim sistemlerinin eski çalışan tarafından kötüye kullanılması riski. | İşletme güvenlik riski | 2 | 4 | 8 | Orta | 1. Çıkışta kart iptali, güvenlik bilgilendirmesi | Dijital erişim log kontrolü yapılmalı ve çalışandan personel kartının zimmet formu ile geri alınması |  | HR / Güvenlik | 2025-12-20
18 | Kritik alanların anahtarlarının kaybolması veya yetkisiz kişilerin eline geçmesi: Depo, metal dedektör, server odası, kamera odası anahtarlarının kontrol dışına çıkması sonucu oluşabilecek güvenlik açığı. | İzinsiz erişim | 2 | 3 | 6 | Düşük | 1. Anahtar envanter listesi, 2. Anahtar teslim formu 3. Anahtar güvenliği prosedürü 4. Günlük güvenlik kontrol listesi | Mevcut önlemlere devam edilecektir. |  | Güvenlik | Sürekli
19 | Açık alan aydınlatmasının arızalanması sonucu gölgeli veya karanlık bölgeler oluşması: Bahçe, otopark ve bina çevresinde görüş zafiyeti oluşması ve güvenlik kameralarının kör noktaya düşmesi riski. | Karanlık alan yaratılması → güvenlik ihlali riski | 3 | 3 | 9 | Orta | 1. 24 saat kamera sistemi ile izlenmesi, konunun anlık fark edilmesi 2. Aydınlatma sisteminin jeneratöre bağlanması 3. Düzenli saha turu | Mevcut önlemlere devam edilecektir. |  | Güvenlik | Sürekli
20 | Forkliftlerin çalışanlara, ziyaretçilere veya kameralara çarpma olasılığı: Malzeme taşıma sırasında hız, görüş kaybı veya yaya–araç ayrımının zayıflığından kaynaklanabilecek kaza riski. | Kamera sisteminin devre dışı kalması | 1 | 4 | 4 | Düşük | 1. Sesli uyarı ve sensör sistemi 2. forklift eğitimi 3. 24 saat kamera sisteminin izlenmesi | Yaya yolları çizilmeli, Kamera bakım planı oluşturulmalıdır |  | IT & Güvenlik | 2025-12-20
21 | Üretim alanında metal parçalarının ürüne karışması: İğne, makine parçaları, metal kırıkları gibi yabancı malzemenin ürün bütünlüğünü ve müşteri güvenliğini tehlikeye atması. | Ürün ve müşteri güvenlik ihlali | 2 | 5 | 10 | Orta | 1. Metal dedektör 2. Düzenli kalibrasyonlar 3. günlük rutin kontroller (2 saatlik) | Mevcut önlemlere devam edilecektir. |  | Kalite ve Son ürün depo müdürü | Sürekli
22 | Server odasına yetkisiz erişim sonucu veri güvenliği ve sistem bütünlüğünün bozulması: IT odasında bulunan kritik sistemlere müdahale, sabotaj veya veri hırsızlığı riski. | Kritik veri/güvenlik erişim riski | 1 | 5 | 5 | Düşük | 1. Kilitli oda, 2. Sadece yetkili giriş | Mevcut önlemlere devam edilecektir. |  | IT | Sürekli
23 | Güvenlik açısından kritik pozisyonlara uygun olmayan personelin atanması: Güvenlik, lojistik, sevkiyat, metal dedektör operatörü ve IT gibi hassas roller için güvenlik geçmişi yetersiz kişilerin seçilmesi. | Yanlış personelin kritik görevlerde çalışması | 2 | 4 | 8 | Orta | 1. Referans kontrolü, 2. Kimlik doğrulama 3. Her 6 ayda bir sabıka kaydının yenilenmesi 4. İşe alım ve işten çıkarma prosedürü | Mevcut önlemlere devam edilecektir. |  | IK | Sürekli
24 | Sevkiyat için gelen kamyonun doğruluğunun teyit edilememesi: Plaka uyuşmazlığı, yanlış araçla yükleme yapılması veya sahte nakliye girişimleri. | Yükün yanlış araca verilmesi, ürün kaybı, güvenlik riski | 1 | 4 | 4 | Düşük | 1. Araç plakası kontrolü | Önceden plaka bildirimi zorunlu hale getirme |  | Lojistik | Hemen
25 | Kargo teslimatlarında şüpheli paket, sahte kurye veya paket değişimi riski: İşletmeye gelen küçük paketlerin içerik açısından kontrolsüz kalması. | Şüpheli paket, sahte kurye, paket değişimi riski | 2 | 3 | 6 | Düşük | 1. Kargo kayıt defteri, 2. Güvenlik kontrolü 3. Kargo ve ziyaretçi prosedürü | Mevcut önlemlere devam edilecektir. Sistemin sürekliliği 3 aylık güvenlik denetimlerinde denetlenmeli |  | Güvenlik | Sürekli

## Score
Risk Önceliklendirme: Riskin önemini tayin etmek amacıyla tahmin edilen riskin verilen risk kriteri ile karşılaştırılması sürecidir
Olasılık / Şiddet | Çok Düşük: 1 | Düşük: 2 | Orta: 3 | Yüksek: 4 | Çok Yüksek: 5 | Risk Puan Aralığı | Risk Önem Derecesi | Açıklama
Çok Düşük: 1 | 1 | 2 | 3 | 4 | 5 | 1-6 | Düşük | Herhangi bir önlem gerekmez
Düşük: 2 | 1 | 4 | 6 | 8 | 10 | 7-11 | Orta | Risk denetim altında tutulmalıdır
Orta: 3 | 1 | 6 | 9 | 12 | 15 | 12-19 | Yüksek | Kök sebep analizi yapılır. Ek önlemler alınması gerekir
Yüksek: 4 | 1 | 8 | 12 | 16 | 20 | 20 ve üzeri | Çok Yüksek | Kök sebep analizi yapılır. Ek önlemler alınması gerekebilir
Çok Yüksek: 5 | 1 | 10 | 15 | 20 | 25
Risk Prioritization: It is the process of comparing the estimated risk with the given risk criterion in order to determine the significance of the risk.
Likelihood / Severity | Very Low: 1 | Low: 2 | Medium: 3 | High: 4 | Very High: 5 | Risk Score Range | Risk Severity | Description
Very Low: 1 | 1 | 2 | 3 | 4 | 5 | 1-6 | Low | No action is required
Low: 2 | 1 | 4 | 6 | 8 | 10 | 7-11 | Medium | The risk should be kept under control
Medium: 3 | 1 | 6 | 9 | 12 | 15 | 12-19 | High | Root cause analysis is conducted. Additional measures must be taken
High: 4 | 1 | 8 | 12 | 16 | 20 | 20 ve üzeri | Very High | Root cause analysis is conducted. Additional measures may be required
Very High: 5 | 1 | 10 | 15 | 20 | 25